## Summary
PEER REVIEW SUMMARY SHEET
REQUEST
Author | Alan DeMars | Date | 2018-12-12
Date | 2018-12-12 | Duration | 1.5
Time | 14:00 | (in hrs.)
EFFORT
S. No. | Reviewer | Preparation | Review
2 | Karl Wecshler | 2.5 | 1.5
3 | Rob Tivy | 2.5 | 1.5
4
5
6
7
8
S. No. | Author |  | Review
1 | Alan DeMars | 0.5 | 1.5
2
3
4
5
DEFECT SUMMARY
TOTAL DEFECTS
CLASSIFICATION BY TYPE |  |  | Count
SEM | Semantic |  | 0
SYN | Syntactic |  | 1
COD | Coding Standards |  | 8
TYP | Typographic |  | 0
DOC | Documentation |  | 5
CLASSIFICATION BY ORIGIN |  |  | Count
REQ | Requirement |  | 0
DES | Design |  | 0
IMP | Implementation |  | 14
STATUS |  |  | Count
COR | Corrected |  | 12
POS | Postponed |  | 0
REM | Remaining |  | 0
NOD | Not really a defect |  | 2
EFFORT SUMMARY
REV | Review effort | (in hrs.) | 9.5
REW | Rework effort | (in hrs.)
Nitya Ramdas, Texas Instruments Santa Barbara |  | Version | 1.0

## Request Form
PEER REVIEW REQUEST
2018-12-12
REQUEST INFORMATION
Date | 2018-12-12
Time | 14:00
Duration | 1.5
AUTHOR(S)
1 | Alan DeMars
2
3
4
5
REVIEWERS
1 | Rob Tivy
2 | Karl Wecshler
3
4
5
6
7
8
REVIEW ITEMS
1 | avala/src/ti/sysbios/family/arm/v8a/smp/Core.xdc
2 | avala/src/ti/sysbios/family/arm/v8a/smp/Core.xs
3 | avala/src/ti/sysbios/family/arm/v8a/smp/Core.c
4 | avala/src/ti/sysbios/family/arm/v8a/smp/Core_asm_gnu.sv8A
5 | avala/src/ti/sysbios/family/arm/v8a/smp/Core__epilogue.h
6 | avala/src/ti/sysbios/family/arm/v8a/smp/Cache.c
7 | avala/src/ti/sysbios/family/arm/v8a/smp/Cache_asm_gnu.sv8A
8 | avala/src/ti/sysbios/family/arm/v8a/smp/CacheMacros.h
9 | avala/src/ti/sysbios/family/arm/v8a/smp/GateSmp.c
10 | avala/src/ti/sysbios/family/arm/v8a/smp/GateSmp_asm_gnu.sv8A
RELATED INFORMATION
1 | Source of Code Review from avala-6.75.01.02_eng
2
3
4
5

## Defect Data
DEFECT RECORD
S. No. | DEFECT DESCRIPTION | ITEM | LOCATION | TYPE | ORIGIN | STATUS | NOTES
|  |  |  | SEM | REQ | COR
|  |  |  | SYN | DES | POS
|  |  |  | COD | IMP | REM
|  |  |  | TYP |  | NOD
DOC
1 | Add comment regarding number of cores supported | 1 | 33 | DOC | IMP | COR
2 | Remove unused configs | 1 | 61, 72, 87, 111, 125, | COD | IMP | COR
3 | Delete unused resetKeystone3 API | 1 | 219 | COD | IMP | COR
4 | Rename startCoreXKeystone3 to startCoreX | 1 | 224 | COD | IMP | COR
5 | Remove unused bootMagicBase and baseClusterId | 2 | 50,51 | COD | IMP | COR
6 | Remove TODO | 2 | 158 | DOC | IMP | COR
7 | Remove TODO | 3 | 199 | DOC | IMP | COR
8 | Make logic easier to follow | 3 | 207 | SYN | IMP | COR
9 | Add :::memory to force code ordering | 3 | 330 | COD | IMP | COR
10 | Is section statement required/used? | 4 | 48 | COD | IMP | NOD | Yes, by A65X gnu linker cmd file
11 | remove TODO | 4 | 115 | DOC | IMP | COR
12 | Since v8a.smp.Cache is identical to v8a.Cache, simply use v8a.Cache | 6.7.8 | all | COD | IMP | COR
13 | Merge CacheMacros content into Cache_asm_gnu.sv78A | 8 | file | COD | IMP | COR
14 | Confirm GateSmp is nodoc'd | 9,10 | all | DOC | IMP | NOD | Yes, it is

## Help
HELP
1 | Description of sheets
1.1 | Summary sheet, as name suggests provides the summary of a review. This sheet is filled at end of the review. Most cells are calculated.
1.2 | Request form is used to provide information regarding the review: date & time of review, name of reviewers, items being reviewed and any additional information e.g. design document(s) can be mentioned as related documents.
1.3 | Defect sheet is used to log the defects in the review items
2 | Logging defects
2.1 | Write the defect inder 'DESCRIPTION'
2.2 | ITEM' refers to the work product in the request sheet.
2.3 | Location can be Line number (in code) or para (in documents).
2.3.1 | Prefix line number with - 'L '
2.3.2 | Prefix page number in document with - 'P '
2.3.3 | Prefix section number in document with 'S '
3 | Defect types
Can be either of - SEM, SYN, COD, TYP
Refer definitions in summary sheet…
4 | Status
Can be either of - COR, POS, REM, NOD, DOC
Refer definitions in summary sheet…
5 | Origin
Can be either of - REQ, DES, IMP
Refer definitions in summary sheet…
6 | Closing defects
Close defects after verifying with one of the reviewers.
Update the rework effort for fixing and verifying the defects (in person hours) including the effort spent by reviewer in verifying closure.
Revision History
v1.0 | Original template
v1.1 | Increased the number of allowed defects to be entered from 50 to 200 in the 'Defect Data' sheet.
v1.2 | Added field for capturing the rework effort based on the corrective action identified in the QST (Quality Steering Team) meeting.
v1.3 | Added the defect type 'DOC' for documentation defects.
v1.4 | Updated summary sheet to add the review effort spent by the author(s). Replaced the 'Comments' with 'Help' information. Provided dropdown list for information on defects.